## READ ME
Calculations Roadmap - Plan, Checkpoints & Tracker
PURPOSE: Working tabs for the calcs & automations practice area. Companion to the 'Gannt' tab; plan of record lives in the Calculations-Project-Planning repo README.
HOW TO GET THESE TABS INTO THE GANNT SHEET: open this file, right-click each tab -> 'Copy to' -> 'Existing spreadsheet' -> pick 'Calculations Roadmap Gannt'. (Drive API access used to create this file cannot edit the existing sheet directly.)
TABS:
Step-by-Step Plan - every step from now to end of year, grouped by phase, with owner, who to engage, target date, and a status dropdown.
Checkpoints - the 7 project checkpoints (aligned to the biweekly Thursday sync). Each lists what to verify and what to decide.
Stakeholders - who on the broader Persefoni team to engage, for what, and when.
Progress Tracker - one row per roadmap item; the tab to update at every biweekly sync (stage, %, status, blockers, last updated).
WORKING RHYTHM: update the Progress Tracker + relevant step statuses at the biweekly Mollie/Evan/Erin sync; walk the Checkpoints tab when a checkpoint date is reached; post a monthly snapshot to #cspa-calculations-and-automations.
HARD DATES (highlighted orange throughout): Simplified electricity - Aug 31, 2026. In-platform gap filling (Liberty Mutual) - Dec 31, 2026.

## Step-by-Step Plan
Step | What & exit criteria | Owner (DRI) | Engage | Target | Checkpoint | Status
PHASE 1 - SHIP THE IN-FLIGHT WORK (Jul-Aug 2026)
1.1 | Hold gap-filling requirements session: reconcile AI-built-tool learnings vs original PRD; split calcs vs advanced workstreams. Exit: agreed scope split. | Mollie | Suhayl, Tai, Evan, Erin | Jul 7 | CP1 | Done
1.2 | Ship spend-based waste: final front-end test + QA sign-off. Exit: live in prod, CS notified. | Evan | Vinh/Huyen (dev); Erin (pre-ship platform pass) | Mid-Jul | CP1 | In progress
1.3 | Update gap-filling PRD (calcs workstream) from session outcomes. Exit: approved by Evan (feasibility) and Erin (customer fit). | Mollie | Suhayl, Tai | Jul 23 | CP1 | In progress
1.4 | Complete eGRID pipeline work (Snowflake/DevOps) and ship. Exit: subregion auto-assignment live. | Evan | Vinh | End Jul-Aug | CP2 | In progress
1.5 | Finalize simplified electricity product guidance. Exit: guidance signed off, no open product questions. | Mollie | Product team, Evan, Erin | Mid-Jul | CP1 | In progress
1.6 | Simplified electricity final dev + testing. Exit: QA sign-off from Evan. | Evan | Vinh, Huyen | Aug 20 | CP2 | In progress
1.7 | SHIP SIMPLIFIED ELECTRICITY - HARD DATE. Exit: live; Erin usability pass done; CS enablement note posted. | Evan | Erin | Aug 31 | CP3 | Not started
1.8 | Draft refrigerants / non-Kyoto requirements. Exit: PRD draft ready for review (passes requirements gate). | Mollie | Erin (methodology), Evan (feasibility) | End Aug | CP2 | Not started
1.9 | Cat 11 scoping: collect AGCO + Tenneco methodology & sample data; join Daimler discussions; untangle region-varying efficiency values. Exit: data in hand, open methodology questions listed. | Mollie | Ben, Caroline, AGCO/Tenneco account teams, Evan | Jul-Aug | CP3 | In progress
1.10 | August code freeze (platform outages): no new code starts; use the month for requirements, testing, validation. | All | - | Aug | - | Not started
PHASE 2 - THE COMMITTED BUILDS (Sep-Nov 2026)
2.1 | DEFRA telework go/no-go: Evan's PRD re-review complete AND window open between electricity ship and gap-filling start. Queue it if window closed. | Evan | Mollie | Sep 3 | CP3 | Not started
2.2 | DEFRA build + test (only if 2.1 = go). | Evan | Vinh/Huyen; Erin (platform review) | Sep | CP4 | Not started
2.3 | Start gap-filling build. Exit: eng kicked off against approved PRD. | Evan | Vinh, Huyen | ~Sep 1 | CP3 | Not started
2.4 | Gap-filling build with biweekly methodology validation against Liberty Mutual's actual use case. | Evan | Erin (validation), Mollie (PRD arbiter), Liberty Mutual account team | Sep-Nov | CP4-5 | Not started
2.5 | Simplified combustion window decision: reconcile 2 vs 3 month estimate; confirm eng can carry it with light support only (else it slides). | Evan | Mollie | Sep 3 | CP3 | Not started
2.6 | Refrigerants start decision: requirements gate passed + light-support slot free (else Dec/Q1). | Mollie | Evan, Erin | Oct 1 | CP4 | Not started
2.7 | Gap-filling health check vs Liberty Mutual date. If at risk: pause everything else, both leads converge. | Mollie | Evan, Erin | Oct 1 | CP4 | Not started
2.8 | Draft Cat 11 PRD from validated three-account methodology (Daimler, AGCO, Tenneco). | Mollie | Erin, Evan, Ben, Caroline | Oct | CP5 | Not started
2.9 | Cat 11 build decision: score against prioritization rubric; slot for Dec/Q1 if it ranks. | Mollie | Evan, Erin, eng | Nov 12 | CP5 | Not started
PHASE 3 - DELIVER & RESET (Dec 2026 +)
3.1 | GAP FILLING FINAL VALIDATION & DELIVERY TO LIBERTY MUTUAL - HARD DATE (end of year). Target internal done: Dec 17. | Evan | Erin, Liberty Mutual account team | Dec 17 / Dec 31 | CP6-7 | Not started
3.2 | CS enablement & docs for all 2026-shipped calcs (electricity, eGRID, spend waste, + fall ships). | Erin | Broader CS team, Mollie | Dec | CP7 | Not started
3.3 | Re-score full backlog with rubric; publish 2027 H1 roadmap. | Mollie | Evan, Erin, product/eng leadership | Dec 17 | CP7 | Not started
3.4 | Start Cat 11 build if greenlit at CP5. | Evan | Vinh, Huyen | Dec/Q1 2027 | - | Not started

## Checkpoints
Checkpoint | Date (biweekly Thu sync) | What we verify | Decisions to make | Who's in the room | Status | Outcome / actions
CP1 | Jul 23 | Spend-based waste shipped; gap-filling PRD updated & approved; eGRID ETA confirmed; electricity product guidance closed. | Any scope changes to gap filling out of the Jul 7 session. | Mollie, Evan, Erin | Upcoming
CP2 | Aug 20 | Electricity on track for Aug 31 (QA status); eGRID shipped; refrigerants PRD draft reviewed. | Escalate electricity if at risk (hard date). Preliminary DEFRA go/no-go. | Mollie, Evan, Erin (+Vinh if pipeline work open) | Upcoming
CP3 | Sep 3 | ELECTRICITY SHIPPED (hard-date verification); gap-filling code started; Cat 11 data collected. | DEFRA final go/no-go. Combustion window decision (2 vs 3 mo reconciled). | Mollie, Evan, Erin | Upcoming
CP4 | Oct 1 | Gap filling on track vs Liberty Mutual date; DEFRA done or queued; combustion progress if running. | Refrigerants start decision. If gap filling at risk: pause everything else. | Mollie, Evan, Erin | Upcoming
CP5 | Nov 12 | Gap filling entering test/validate; Cat 11 PRD drafted and scored. | Cat 11 build decision (Dec/Q1 slot). | Mollie, Evan, Erin + eng as needed | Upcoming
CP6 | Dec 10 | Gap-filling final validation plan; Liberty Mutual delivery logistics; CS enablement drafted. | Confirm delivery date with Liberty Mutual account team. | Mollie, Evan, Erin, LM account team | Upcoming
CP7 | Dec 17 | GAP FILLING DELIVERED (hard-date verification); 2026 retro; 2027 H1 roadmap published. | 2027 H1 commitments. | Mollie, Evan, Erin, product/eng leadership | Upcoming

## Stakeholders
Name / group | Role | Why engaged (expertise) | Engage for | When
Mollie Carroll | PM / requirements owner (CS) | Methodologies, technical requirements | All PRDs, prioritization, checkpoint facilitation, cross-team coordination | Always
Evan Kutter | Calc support lead; directs eng | Calculations engineering, testing, QA | Build DRI on every major item; QA sign-off; directs Vinh & Huyen | Always (~0.8 FTE plannable)
Erin Dickinson | Calc support lead | Customer needs, platform use, methodologies | Intake scoring (demand + CS time saved), methodology review, pre-ship usability pass | Every item (~6 hrs/wk)
Vinh | Engineer (directed by Evan) | Snowflake / DevOps pipeline; platform dev | eGRID pipeline; electricity + gap-filling builds | Per Evan's direction
Huyen | Engineer (directed by Evan) | Platform dev | Electricity, gap-filling, and fall builds | Per Evan's direction
Suhayl | Gap-filling SME | AI-built gap-filling tool learnings | Requirements sessions; PRD review | Jul (session held Jul 7) + as needed
Tai Le | Gap-filling SME | Gap-filling requirements | Requirements sessions; PRD review | Jul + as needed
Ben | Daimler account | Cat 11 customer context | Daimler methodology/sample data; customer discussions | Jul-Oct (Cat 11 scoping)
Caroline Bartlett | Daimler account | Cat 11 customer context | Daimler methodology/sample data; customer discussions | Jul-Oct (Cat 11 scoping)
AGCO & Tenneco account teams | Account teams | Cat 11 demand at their accounts | Methodology + sample data (region-variable fuel use; weight apportioning) | Jul-Aug
Liberty Mutual account team | Account team | Gap-filling committed customer | Use-case validation during build; delivery coordination | Sep-Dec
Product team (contact TBD) | Product | Product guidance & roadmap alignment | Simplified electricity guidance (Jul); quarterly re-prioritization | Jul; quarterly
Broader CS team | #cspa-calculations-and-automations | Frontline customer workarounds | Intake of new items (channel template); enablement on shipped calcs | Ongoing; monthly snapshot

## Progress Tracker
Item | Pipeline stage | DRI | % complete | Priority score | Hard date | Next checkpoint | Status | Blockers / notes | Last updated
Spend-based waste | Test & validate | Evan | 85% | 2.95 |  | CP1 Jul 23 | On track | Front end in dev/test; ships mid-Jul | 2026-07-08
eGRID subregion assignment | Build | Evan | 70% | 3.2 |  | CP1 Jul 23 | On track | Snowflake/DevOps pipeline pieces with Vinh | 2026-07-08
Simplified electricity | Build | Evan | 60% | 4.35 | Aug 31, 2026 | CP2 Aug 20 | On track | Needs product guidance closed; final dev + testing | 2026-07-08
Simplified combustion | Build (eng-led) | Evan (light touch) | 50% | 3.15 |  | CP3 Sep 3 | Not started | Reconcile 2 vs 3 month estimate; runs only if light-support | 2026-07-08
Refrigerants / non-Kyoto | Requirements | Mollie (PRD) / Evan (build) | 25% | 2.8 |  | CP4 Oct 1 | Not started | PRD to draft by end Aug; fails requirements gate until then | 2026-07-08
DEFRA telework | Requirements | Evan | 20% | 2.55 |  | CP3 Sep 3 | In progress | PRD re-review underway; go/no-go depends on Sep window | 2026-07-08
In-platform gap filling | Requirements | Evan (build) / Mollie (PRD) | 0% | 4.35 | Dec 31, 2026 | CP1 Jul 23 | On track | PRD update from Jul 7 session; code start ~Sep 1 | 2026-07-08
Category 11 | Intake / scoping | Mollie | 0% | 2.85 |  | CP5 Nov 12 | In progress | Collecting AGCO/Tenneco data; Daimler efficiency-value oddities open | 2026-07-08